## Slide 1: MCC: Scheduling & PEWs Steve Blackshaw & Sam Clark
The following slides articulate the concepts that BTW is currently considering within its scheduling and PEWs function design for the MCC. Its purpose is to seek feedback/dialogue with Communication Providers on these concepts following the recent consultation (C21-IM-008)

## Slide 2
Apr
May
Jun
Jul
Aug
Oct
Sep
Nov
Dec
Feb
Jan
Mar
Apr
May
Mar
Jun
Jul
Jan
Feb
On-the-Night Cutovers
Schedule into MCC control; W/C dates published to CPs; CPs have 3 weeks to raise CRs
3 wks to assess CRs & respond; amend Schedule if necessary (amended sites stay in quarter if poss.)
PEWs issued at -21 days from each DLE catchment area or DSLAM site grooming; TCP fit or Cutover
3 wks to assess CRs & respond; Schedule amended if necessary (amended sites stay in week if poss.)
OTN (On-The-Night) dates to CPs; CPs have 3 weeks to raise CRs
Grooming & TCP Fitting activity
Schedule Fixed (when OTN dates are fixed, only “life & death” / “blue light” / emergency changes allowed
Schedule Management
PEW Issue & Manage
Activities (Groom, TCP, Cutover)
PEWs Management during activity
W/C fixed
OTN fixed

## Slide 3
Apr
May
Jun
Jul
Aug
Oct
Sep
Nov
Dec
Feb
Jan
Mar
Apr
Mar
Jan
Feb
May
Jun
Jul
200 sites being groomed
200 sites having TCPs fitted
200 sites being migrated *
* Based on average 10 conc units per DLE
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed
W/C fixed
OTN fixed

## Slide 4
PEW Clarify
PEW Clarify
Day 1
Pathfinder
Phases 1&2
PSTN
End-Customer
Migration Only
Emails to CPs
MCC
Manual
Activity
(Nov 06)
PEW Clarify
IRAMs
21C CP
Web
Portal
Day 2
Pathfinder
Phase 3
Unified PEW Process
PSTN
BB
End-Customer
Migration Only
Access enables
CPs to
“come & look”
Emails to CPs
MCC
Manual
Activity
(Feb 07)
TEWT
PEW Clarify
IRAMs
21C CP
Web
Portal
RSS feed
Day 3
National
Migration
Unified PEW Process
PSTN
BB
Grooming,
TCP fit,
End-Customer
Migration
(Mar 07)
Day 0
Wick POTS only
PSTN
End-Customer
Migration Only
(Oct 06)
NPW Team informs BT Wholsale

## Slide 5: Summary
New 21CN Industry Web Portal
  Migration Schedule releases, changes & latest PEW information
PSTN PEW Notification Process
  developed to mirror the existing Broadband / DSLAM process
Existing BB PEW Email Notification Process (including PSTN)
  enhanced to provide RSS feeds via the web portal.
“Blanket PEWs for Grooming & TCP fit”
  weekly or fortnightly time periods listing a number of sites
  recognises the very low impact & outage times incurred by this work which is analogous to everyday provision & maintenance activity across the UK telecoms networks.
existing PEW process continues for End-Customer “On the Night” migrations
  i.e. 00:00 to 06:00 on a specified date per DLE or DSLAM site.
The Migration Plan Change Request & Dispute Process
  will include an Emergency Change Request (ECR) process for changes within the last few weeks of migration

## Slide 6: Issues for discussion
How do we build a database of who/which CP interfaces we need to inform of PSTN PEWs?